## QA
ALPSALPINE CONFIDENTIAL
No. | 質問者が記載する項目 | [7 empty] | 回答者が記載する項目 |  |  |  | Note
| ステート | 分類 | 日付 | 納期 | 所属 | 名前 | 関連文書 | 質問 | 回答 | 日付 | 所属 | 名前
1 | Open | 要求仕様 | 2026-05-25 | 2026-05-27 | 第2回路技術部 | 森崎 |  | 「要求仕様」シートを更新しました。下記青字で追記してますので、追加でご回答お願いします。 ■更新内容 1) 電源追加 2) 消費電流追加 3) 開発状況の補足追記 4) Bluetooth SIG認証追加 | 1) Generally, chips require 1.8V or 3.3V, but modules use a single 3.3V module. 2) Currently, the maximum operating current of the chip is understood to be <1.0A.Sleep mode :0.41mA(AW611) 3) AW611 BT 5.x are now ready; BT 7.0 (AW722) samples are expected in 2027, MP: 2028. 4) A&W Bluetooth stack: V5.4 (ready), V6.3 (2026/E), V7.0 (2027/Q3) A&W Bluetooth profile package: ready For the power supply specifications of the chip, it's best to confirm the usage information with the chip manufacturer for the most accurate details. Bluetooth chip: BT 5.x (AW611 ready), BT 7.0 (AW722 2028/02)
2 | Open | アンテナ | 2026-05-25 | 2026-05-27 | 第2回路技術部 | 森崎 |  | 製品全体のアンテナ数を3本にすべきか、それとも2本でいけるのか分かっておりません。AA/CP用に2本、Beacon / Channel Sounding / Find Myなど常時BLE実施するBLEチップ用に1本で、合計3本が理想だと思います。しかしながら、製品に3つアンテナを乗せるのは厳しく、2本が妥当だと考えています。その場合、AA/CP用のアンテナが1本となり、下記気になる点がございますので、ご回答よろしくお願いします。実績ベースでも構いません。 ■質問 1) ご紹介頂いたICは、アンテナ1つでAA/CP認証が取れる性能はございますか？実績ベースでも構いません。 2) バイクは屋外なので国によっては5GHzが使えず、CPでは2GHz-MIMO必須になると思います。その場合、アンテナ1つだとMIMOができず2.4GHz-SISOしかできません。その場合でも、Waiver申請などで認証取得した実績などございますか？ 3) 上記実績が無い場合、そのような国ではAA同様に無線は諦めて有線のみ対応とするのが通例でしょうか。 | Based on our extensive project experience, if a chip supports dual antennas, a dual-antenna design is always preferred. This is primarily to mitigate the potential impact of Bluetooth/Wi-Fi coexistence. 1) Currently, dual-antenna setups are frequently used because AA (Android Auto) wireless version 2.5 and later requires Wi-Fi AA to operate on the 5GHz band, while Bluetooth uses 2.4GHz. Therefore, dual-antenna designs have become the primary choice. 2) According to information we received from the test Lab, it is recommended to select support for both Wi-Fi 5GHz and 2.4GHz during CarPlay certification ,of course if use one Antenna maybe not suitable . 3) This approach is feasible.from test Lab data shows that some customers support 5GHz only, but switch to wired CarPlay in countries where 5GHz is not permitted." If you need more information about certification, we will consult the relevant certification lab.
3
4
5

## 要求仕様
要求仕様
Comboチップのみのご提案、可能であればComboチップ + BTチップ(BLEが高機能)の両方で下記要件を満たせる構成でご提案よろしくお願い致します。
区分 | 項目 | 要求 | 補足 | ご回答内容
Bluetooth | version | 1) ver 5.x 2) ver 6.0以上 3) ver 7.0以上 | 3パターンの提案をお願いします。 各パターンにおけるコスト差および消費電力の差分もご提示ください。 ver 6.0以上がMust ver 7.0以上がWant ver 5.xはコストダウン案としてご提案頂ければと思います。 | For BT stack is OK . As we talk with chip maker like NXP , Infineon current chips all support 5.x, and will directly support 7.x in the future. There are no plans for BT 6.x; 7.x will be available in 2027.
Bluetooth | Class | Class 2 | Class 1相当のレベルまで強化できるか否かに関しまして、併せてご回答お願いします。 | Yes , the chip supports it.
Bluetooth | 同時ペアリング数 | BLE x 5台 BTC x 5台 | ペアリングに加えて、記憶できる数になります。 | ok
Bluetooth | BLEとBTCの同時使用 (デュアルモード) | あり |  | ok
Bluetooth | BLEのCen./Peri.を独立制御 (デュアルロール) | あり |  | ok
Bluetooth | BTプロファイル | 「BTプロファイル」シートの項目を満たすこと |  | ok
Bluetooth | LE Secure Connections | あり | Encryption of BLE messageも必要になります | ok
Bluetooth | LE 2M PHY | あり |  | Yes
Bluetooth | Channel Sounding | あり |  | ok ( BT Module also need support,NXP AW722 will support 2027)
Bluetooth | OOB(Out Of Band)ペアリング | あり | QRコード表示を想定しています | ok
Bluetooth | Advertising Extensions | あり |  | ok
Bluetooth | Apple Find My / Google Find My Device | あり | 必須ではなく、オプション扱いになります | ok ( Customers must obtain authorisation from Apple/Google )
Bluetooth | Isochronous Channels (LE Audio) | あり | 必須ではなく、オプション扱いになります | ok ( BT Module also need support ,like AW611,AW693,CYW89570)
Bluetooth | Call Control Profile(CCP) | あり | 必須ではなく、オプション扱いになります | ok
Bluetooth | Privacy(Resolvable Private Address) | あり | 必須ではなく、オプション扱いになります | ok
Wifi | 規格 802.11b/g/n (Wi‑Fi 4) 802.11ac (Wi‑Fi 5) 802.11ax (Wi‑Fi 6 / 6E) | 802.11ac (Wi‑Fi 5) | AA/CP要件を満たす必要があります。 | Currently, chips from NXP and Infineon are referenced and can support this.(like AW611,AW693,CYW89570)
Wifi | 対応周波数 | 2.4GHz + 5GHz | W52 / W53 / W56対応 ※日本の屋外で5GHzを使用するケースも想定 | N/A
Wifi | MIMO | あり | MIMOが必須ではなくなる可能性がございますので、MIMOなしについて提案お願いします。 | N/A
Wifi | DFS | あり |  | N/A
Wifi | ロール | AP/STA | AP：スマートフォン想定 STA：OTA想定 | Currently, chips from NXP and Infineon are referenced and can support this.(like AW611,AW693,CYW89570)
Wifi | セキュリティ規格 | WPA3 Personal Transition | AA/CP要件を満たす必要があります。 | Currently, chips from NXP and Infineon are referenced and can support this.(like AW611,AW693,CYW89570)
General | 電源 | 特になし | 必要な電源の数と電圧値を教えてください。 | Take AW611 as an example : There is a difference between using a chip and a module: AW611 chip: 1.8V and 3.3V; AW611 module: 3.3V.
General | 消費電流 | 消費電流：ECU全体で1.5A 待機電流：ECU全体で100uA | 通常動作時のmax値と待機時のmax値を教えてください。 | Taking the AW611 as an example, the current is below 1.0A, and the deep sleep mode is 0.41mA. Since we don't have test data from various chip manufacturers, this is just based on the datasheet we have.
General | インターフェース | BT: UART / I2S Wifi: SDIO |  | Most combo chip BT support UART/I2S , if WiFi interface only SDIO,(AW611 ,CYW89570)
General | 動作保証温度 | -40℃~+105℃ |  | NXP,Infineon Automotive grade chip suport (sucjh as AW611,AW693,CYW89373,CYW89570)
General | コネクテッドカー規制 | 規制対象外であることが必須 |  | N/A
General | 開発状況 | 2027/2/Fまでに試作用サンプルを納品できること | ES/CS/MPの時期を教えてください。すでに量産中の場合、量産中という文言だけでOKです。 | AW611,AW693,CYW89373,CYW89570 : production AW722 : Sample : 2027/02 , MP:2028/ end of Q2
General | Bluetooth SIG認証 | 必須 | 取得状況について教えてください。未取得の場合、いつ取得見込みか教えてください。 | A&W Bluetooth stack: V5.4 (ready), V6.3 (2026/E), V7.0 (2027/Q3) Bluetooth profile package: ready Chip : AW722 BT 7.0 SIG Certification plan 2028/02
General | Automotive対応 | 必須 | AEC対応が必須ではないです。御社内でAutomotive品として開発しているものであればOKです。 | ok
AA/CP: Android Auto / CarPlay
Note : The text in black is related to "Chip" and represents our answers after inquiry; it is provided for reference. N/A : It relates to the chip's detailed design specifications or plans; we are still inquiring.

## BTプロファイル
Bluetoothプロファイル一覧
Bluetooth profile | Description | A&W
BLE HID | Send switch operation from the vehicle to smartphone by HID over GATT. Used as a primary input mechanism from Meter to smartphone. | OK
BLE Battery | Notification of smartphone and/or vehicle battery status between smartphone and Meter. | OK
BLE Current Time | Synchronization of clock information between smartphone and Meter. | OK
BLE Device Information | Exchange of BTU version, Meter type, and device identification information with smartphone. | OK
BLE CCP (Optional) | Bluetooth LE Audio framework-based Call Control Profile. Provides call answer/end and mute signaling over BLE. | OK
BLE LE Audio (Optional) | Reserved for future extension of audio or media-related functions using BLE profile. | OK
AMS (iOS) | Apple Media Service for iOS to obtain media playback status and metadata via BLE. Used as a complement to standard media control functions. | OK
ANCS (iOS) | Apple Notification Center Service to receive notification information from iOS devices via BLE. | OK
Custom BLE Profile – Initialization | Initialization sequence and exchange of vehicle status and device/software version during connection setup. | OK
Custom BLE Profile – Vehicle Identification | Identification of vehicle type and installed equipment by smartphone application. | OK
Custom BLE Profile – UI Control | Control of screen icon, popup status, and UI behavior on the Meter depending on switch operation. | OK
Custom BLE Profile – Firmware Update | Firmware update mechanism for BTU/Meter using BLE. | OK
Custom BLE Profile – Security | Encryption key exchange and secure communication setup between smartphone and Meter. | OK
Custom BLE Profile – Screen/Icon Update | Update and addition of screen icons and UI resources on the Meter. | OK
Custom BLE Profile – Vehicle Data Transfer | Transfer of vehicle-related data from Meter to smartphone. | OK
Custom BLE Profile – Meter Configuration | Update of Meter configuration parameters from smartphone. | OK
Custom BLE Profile – Image Data Transfer | Transfer of application-generated image data from smartphone to Meter. BLE is the only communication method used for image data transfer; Bluetooth Classic is not used for this purpose. | OK
Custom BLE Profile – External Sensor Data | A custom BLE profile for acquiring numerical data and status information from add-on BLE sensor devices (e.g., TPMS). The profile shall support both periodic data transmission and event-based notifications, and the meter shall be capable of receiving, displaying, and linking the acquired data to other functions. | OK
Classic AVRCP | Media control and media metadata retrieval for smartphones. Used to obtain playback status and cover art information from both Android and iOS devices, enabling a unified media UX on the Meter across platforms. | OK
Classic HFP (Hands-Free Profile) | Hands-free call control for smartphones. Enables call answer/end operations initiated from the Meter, including interaction with voice assistant functions (e.g. Siri on iOS), in order to harmonize call operation UX between Android and iOS devices. | OK
Classic Audio / Media Extension (Optional) | Reserved for future extension of audio or media-related functions using standard Bluetooth Classic profiles. This profile is not used for application data or image transfer. | OK
Other : Notification of smartphone status such as Wifi and lTE communication strength will be added.