## Cover
Advanced & Wise Tech. Corp. 雅迪(2W) Project Work Breakdown Sheet
Template Information
Doc. No.
| Document Name | Project Schedule
| Version | 1.0
| Level of confidentiality | ■Confidential □Internal use □Public
|  | Name | Date
| Develop by | tianjunjie | 2024-10-10
Review by
Approve by
Template History
| Version | Date | Author | Description
| 1.0 | 2024-10-10 | tianjunjie | Initial of the template

## History
Date | Version | Descriptions | Editor
2026-02-06 | 0.1 | Draft

## Project Schedule
Phase (Mark) | Index | Activity | Sub-Activity | Additonal Note | Dependency | Plan |  |  | Actual
[6 empty] | Start Date | End Date | Owner | Start Date | End Date | Status
Project
P0 |  | Before Kick Off
| 1 | 专案需求
| 1.1 |  | Marketing Research |  |  |  |  | john |  |  | closed
| 1.2 |  | PM Request Form |  |  |  |  | john
kick off meeting check list
| 2 | Kick-Off |  |  |  | 2026-02-06 | 2026-02-06 | tianjunjie
P1 |  | Planning
| 1 | SPEC Clarification
| 1.1 |  | project member
| 1.2 |  | project check list | [5 empty] | 2026-02-06 | 2026-02-10
S/W 需求发展与分析 - SRS(S/W Requirement SPEC)
Functional Requirement - Common functions
Functional Requirement - HFP/PBAP/A2DP/AVRCP/SPP functions
Non-functional Requirement
SW test plan
Development Plan
提出产品设计/开发计划
P2 |  | Product Design/Development
Design
API SPEC-Common
API Spec-HFP/PBAP/A2DP/AVRCP/SPP
Development
| 2.1 | 主驾 | Implemented based on Bluetooth - Common |  |  |  |  | quanchao
| 2.2 |  | Implemented based on Bluetooth - HFP |  |  |  |  | quanchao
| 2.3 |  | Implemented based on Bluetooth - AVRCP |  |  |  |  | quanchao
| 2.4 |  | Implemented based on Bluetooth - A2DP |  |  |  |  | quanchao
| 2.5 |  | Implemented based on Bluetooth - PBAP |  |  |  |  | quanchao
| 2.6 |  | Implemented based on Bluetooth - SPP |  |  |  |  | quanchao
| 2.7 |  | Implemented based on Bluetooth - MAP |  |  |  |  | quanchao
| 2.8 |  | Implemented based on Bluetooth - BLE |  |  |  |  | quanchao
| 2.9 | 副驾 | Implemented based on Bluetooth - Common |  |  |  |  | quanchao
| 2.1 |  | Implemented based on Bluetooth - HFP |  |  |  |  | quanchao
| 2.11 |  | Implemented based on Bluetooth - A2DP |  |  |  |  | quanchao
Integration
|  |  | Integration Test - Common/HFP/PBAP |  |  |  |  | sunnan
|  |  | Integration Test - A2DP/AVRCP/SPP |  |  |  |  | sunnan
Problem resolving - Common/HFP/PBAP
Problem resolving - A2DP/AVRCP/SPP
Regression test
P3 |  | Product
正式版本发布
P4 |  | Project Closure
Project Closure Meeting

## project check list
ID | Initiator | Issue Date | Detail | Status | Answer | Note
| tianjunjie |  | stack版本
| tianjunjie |  | SDK版本
| tianjunjie |  | 是否有template提供给客户
| tianjunjie |  | 拿到硬件之前，ANW可以做哪些工作？

## project member
role | Name
Project Management | Junjie
SW Leader | Yingbin
Project Leader | QuanChao
SW Engineer | ZhanXu、 zhaozunqiang
SW Engineer | Nick Chen
Sales | Jason
QA | Sunnan